## Slide 1: Transnational Meeting no. 4 Krsko (Slovenia)
Executive Summary
Covered first year of the project
1st year (1 Sept. 2015 - 1 Sept.2016)
Basic Drone is developed. This cover the first three Intellectual Outputs, now we need to develop the reports and publish
Progress report was addressed to Spanish National Agency (July 2016)
Highlight the good cooperation and willingness of all partners in the project :-)

## Slide 2: Transnational Meeting no. 4 Krsko (Slovenia)
Executive Summary
1st year (1 Sept. 2015 - 1 Sept.2016)
We have developed the website, social media channels.
We have known and selected components for our first drone. We have made 3D design & 3D printing, tests, explore software, etc.
Events have been mounted in some Schools about drones.
We had assisted as project example in Erasmus + 2016 call in Spain.
This is the 4th transnational meeting. We have visited all participating countries. We are travelling usually with two teachers and two students per meeting.

## Slide 3: Transnational Meeting no. 4 Krsko (Slovenia)
Executive Summary
Develops Advanced drone
2 Transnational meetings in Croatia and Slovenia
Interim Report: Deadline February 2017 => 40% funding 30 days after positive evaluation by Spanish National Agency.
Movility Tool+ (Coordinator with support of all partners)
Results (First Intellectual Outputs published)
Following Dissemination Plan: website, social media, internal presentations in Schools and more …
Multiplier Event in Tehnogenij fair 2017. (20 Slovenian participants)
2nd Year (Sept. 2016-Sept 2017)

## Slide 4: DroneTeam project:
9 DroneTeam Intellectual Outputs: OER -1- Basic Toy drone frame OER-2 - Module of Flight Control OER-3 - Module of Communication Control OER-4- Module of Advanced frame OER-5- Module of GPS/Compass Control OER -6 - Module of Problem Management OER-7 - Module of Flight Stabilization System OER-8 - Module of First Person View O9: MOOC Course. Multiplier events all partners
Fist Drone
Second Drone
Multiplier Event Krsko
Multiplier Event Foia

## Slide 5: DroneTeam project:
1st year
Basic Drone
1st – 3rd Intellectual Outputs
2nd year
Advanced Drone
4th -8th Intellectual Outputs
3rd year
Personalised Drone
9th IO - Do it Yourself (elearning course)